## 角色需求进度总表 (hidden)
需求描述 | 类别 | 音效名 | 进展状态 | 优先级 | 限定武器 | 版本 | 需求方（策划） | 跟进人（音频） | 提出时间 | 目标交付日期 | 相关文件 | 父记录 | 样本数量 | 技能播放方式 | 声音绑定方式 | *编辑器配置文件名
女士跟鞋（正常体型） | FS |  | 进行中 | [5 empty] | 2023-07-25 | 2023-08-01 |  | 角色通用脚步声-第一批
男士皮靴 | FS |  | 后置 | [5 empty] | 2023-07-25 | 2023-08-01 |  | 角色通用脚步声-第一批
女士低跟鞋（萝莉体型） | FS |  | 后置 | [8 empty] | 角色通用脚步声-第一批
穿刺 | Imp |  | 进行中 | [8 empty] | 角色通用武器命中库-第一批
斩击 | Imp |  | 进行中 | [8 empty] | 角色通用武器命中库-第一批
钝击 | Imp |  | 进行中 | [8 empty] | 角色通用武器命中库-第一批
cloth | Foley |  | 排期中 | [8 empty] | 通用Foley音效素材库制作
角色通用武器命中库-第一批 | Imp |  | 进行中 |  |  | Q4
角色通用脚步声-第一批 | FS |  | 进行中 | P2 |  | Q4 |  |  | 2023-07-25 | 2023-08-01 | 相关文件.docx
白银装甲 | Foley |  | 排期中 | [8 empty] | 通用Foley音效素材库制作
沟通确认需求 | [8 empty] | 2023-11-03 |  |  | 主角雾宁技能音效
音效制作 | [11 empty] | 主角雾宁技能音效
整合测试 | [11 empty] | 主角雾宁技能音效
反馈修改 | [11 empty] | 主角雾宁技能音效
液体白银音效库 | Foley |  | 后置 |  |  | Q3
集成杜比沉浸式全景声音频 | 技术 |  | 后置 |  |  | 2024
富婆萝莉 | 角色 |  | 后置 |  |  | Q4
骑士库拉蒂技能音效 | 角色 |  | 前置未完成 |  |  | Q4
雷可司技能音效 | 角色 |  | 前置未完成 |  |  | Q4
通用Foley音效素材库制作 | Foley |  | 排期中 | P2 | [6 empty] | 相关文件.docx
主角雾宁技能音效 | 角色 |  | 排期中 | P0 | 双手剑 | Q4 |  |  |  |  | 相关文件.docx |  | 49
灰姑娘技能音效 | 角色 |  | 前置未完成 |  |  | Q4
通用素材库录制 | Foley | [10 empty] | 液体白银音效库
标准处理和后期 | Foley | [10 empty] | 液体白银音效库
特效音频处理尝试 | Foley | [10 empty] | 液体白银音效库
预研报告并输出第一版方案 | 技术 |  | 验收完成 |  |  | Q3 |  | 陈开萱 | 2023-08-14 | 2023-08-22 |  | 集成杜比沉浸式全景声音频
demo尝试 | 技术 |  |  |  |  | 2024 | [5 empty] | 集成杜比沉浸式全景声音频
混音并集成（PC及主机） | 技术 |  |  |  |  | 2024 | [5 empty] | 集成杜比沉浸式全景声音频
混音并集成（手机） | 技术 |  |  |  |  | 2024 | [5 empty] | 集成杜比沉浸式全景声音频
角色脚步和命中的整合及debug |  |  | 验收完成 |  |  | Q4 |  | 陈开萱 | 2023-08-02 | 2023-08-25
排期中
角色通用foley声-特殊移动 |  |  | 进行中
女仆技能音效 | 角色 |  | 进行中 |  |  | Q4
沟通确认需求 |  |  | 进行中 | [8 empty] | 女仆技能音效
音效制作 |  |  | 进行中 | [8 empty] | 女仆技能音效
整合测试 |  |  | 进行中 | [8 empty] | 女仆技能音效
反馈修改 |  |  | 进行中 | [8 empty] | 女仆技能音效
cloth |  |  | 进行中 | [8 empty] | 角色通用foley声-特殊移动
白银装甲 |  |  | 进行中 | [8 empty] | 角色通用foley声-特殊移动
排期中

## Boss&Monster需求进度总表 (hidden)
需求描述 | 名称（技能编辑器的技能名） | 多行文本 8 | 装甲属性 | 技能描述说明 | 音效名 | 进展状态 | 优先级 | Boss级别 | 版本 | 需求方（策划） | 跟进人（音频） | 提出时间 | 目标交付日期 | 相关文件 | 父记录 | 样本数量 | 技能播放方式 | 声音绑定方式 | *编辑器配置路径
[6 empty] | 验收中 | P0 | [6 empty] | 相关文件.docx
狼人 |  |  | 生物（斩击） |  |  | 排期中
[6 empty] | 排期中 | P2 | [6 empty] | 相关文件.docx
蜡烛人 |  |  | 生物（斩击） |  |  | 前置未完成 | P0 | 特殊剧情BOSS |  |  |  | 2023-03-01 | 2023-06-01 | 相关文件.docx
[6 empty] | 验收中 | P1 | [6 empty] | 相关文件.docx
[6 empty] | 进行中 | P1 | [6 empty] | 相关文件.docx
验收中
铁甲面 |  |  | 机械（钝击） |  |  | 前置未完成
小蜡烛人 |  |  | 生物（斩击） |  |  | 前置未完成
蜡烛头 |  |  | 生物（斩击） |  |  | 前置未完成
鹰身女妖 |  |  | 生物（斩击） |  |  | 前置未完成
发条无人机 |  |  | 机械（钝击） |  |  | 前置未完成
樱桃树 |  |  | 生物（斩击） |  |  | 前置未完成
灰姑娘 |  |  | 人类（穿刺） |  |  | 前置未完成 |  |  | Q4
前置未完成

## Hero（技能）
需求版本 | 需求模块 Require Module | 二级模块 Second Module | 需求名 Require Name | *音频配置位置（动画animation） | *音频配置位置（技能编辑器） | 需求描述 Skill Description | 音频状态 Status | 原音效名Old | 原音效名 | 音效名 Sample Name | 参考视频名称 Video | 音效描述 Sound event Description | 音频交付时间 Due Time | 样本数量 Sample Number | 技能播放方式 One shot/Loop | 声音绑定方式 Sound Binding Method | 备注 Remarks | 样本问题及优化方向 V1 | 补充 V1 | 样本问题及优化方向 V2 | 补充 V2 | 样本问题及优化方向 V3 | 补充 V3 | 样本问题及优化方向 V4 | 补充 V4 | 样本问题及优化方向 V5 | 补充 V5
[8 empty] | 音效类型Skill or Action_角色名_武器_技能名_拆分 | 音效类型Skill or Action_角色名_武器_技能名_拆分 | Char_Skill_CXX_技能名称_状态 |  | 【角色】女主：雾宁音效设计
Y1Q4 | C01女主雾宁 | 普通攻击连击 | 1段开始 | AN_Munin_TwinBlade_C_A_Attack1_F | Munin_Attack1 | 女主的普通攻击：挥动双头剑向前方进行斩击，共四段 | in progress | Skill_Munin_TwinBlade_Attack1 | Char_Skill_C01_Atk1 | Char_Skill_C01_Atk1
|  |  | 1段劈砍 |  |  |  | in progress |  |  | Char_Skill_C01_Atk1_2nd
|  |  | 1段结束 |  |  |  | in progress |  |  | Char_Skill_C01_Atk1_End
|  |  | 2段开始 | AN_Munin_TwinBlade_C_A_Attack2_F | Munin_Attack2 |  | in progress | Skill_Munin_TwinBlade_Attack2 | Char_Skill_C01_Atk2 | Char_Skill_C01_Atk2
|  |  | 2段第二段劈砍 |  |  |  | in progress |  |  | Char_Skill_C01_Atk2_2nd
|  |  | 2段结束 |  |  |  | in progress |  |  | Char_Skill_C01_Atk2_End
|  |  | 3段开始 | AN_Munin_TwinBlade_C_A_Attack3_F | Munin_Attack3 |  | in progress | Skill_Munin_TwinBlade_Attack3 | Char_Skill_C01_Atk3 | Char_Skill_C01_Atk3
|  |  | 3段第二段劈砍 |  |  |  | in progress |  |  | Char_Skill_C01_Atk3_2nd
|  |  | 3段第三段劈砍 |  |  |  | in progress |  |  | Char_Skill_C01_Atk3_3rd
|  |  | 3段结束 |  |  |  | in progress |  |  | Char_Skill_C01_Atk3_End
|  |  | 4段开始 | AN_Munin_TwinBlade_C_A_Attack4_F | Munin_Attack4 |  | in progress | Skill_Munin_TwinBlade_Attack4 | Char_Skill_C01_Atk4 | Char_Skill_C01_Atk4
|  |  | 4段第二段劈砍 |  |  |  | in progress |  |  | Char_Skill_C01_Atk4_2nd
|  |  | 4段第三段重击 |  |  |  | in progress |  |  | Char_Skill_C01_Atk4_3rd
|  |  | 4段结束 |  |  |  | in progress |  |  | Char_Skill_C01_Atk4_End
|  | 闪避/冲刺攻击 | 冲刺接普攻 |  | Munin_RushAttack |  | in progress | Skill_Munin_TwinBlade_RushAttack | Char_Skill_C01_Atk_Rush | Char_Skill_C01_Atk_Rush
|  |  | 冲刺后第二段突刺 |  |  |  | in progress |  |  | Char_Skill_C01_Atk_Rush_2nd
|  |  | 冲刺接普攻结束 |  |  |  | in progress |  |  | Char_Skill_C01_Atk_Rush_End
|  |  | 闪避接普攻 |  | Munin_RushAttack_Step |  | in progress |  |  | Char_Skill_C01_Atk_Rush_Step
|  |  | 闪避后第二段突刺 |  |  |  | in progress |  |  | Char_Skill_C01_Atk_Rush_Step_2nd
|  |  | 闪避接普攻结束 |  |  |  | in progress |  |  | Char_Skill_C01_Atk_Rush_Step_End
|  | 蓄力 | 派生-蓄力特效 |  | Munin_Focus_FromReadyN（多段State) Munin_Focus_FromReadyR（多段State） | 冲刺进蓄力/直接进蓄力 | in progress |  |  | Char_Skill_C01_Focus_Ready
|  |  | 派生-蓄力攻击1-起手 | AN_Munin_TwinBlade_C_A_FocusAttack1 |  | 水平击飞 | in progress | Skill_Munin_TwinBlade_FocusAttack1 | Char_Skill_C01_Focus_Atk1 | Char_Skill_C01_Focus_Atk1 | [7 empty] | 砸下来的反馈
|  |  | 派生-蓄力攻击1-2段 |  |  |  | in progress |  |  | Char_Skill_C01_Focus_Atk1_2nd
|  |  | 派生-蓄力攻击1-3段 |  |  |  | in progress |  |  | Char_Skill_C01_Focus_Atk1_3rd
|  |  | 派生-蓄力攻击1-4段 |  |  |  | in progress |  |  | Char_Skill_C01_Focus_Atk1_4th
|  |  | 派生-蓄力攻击1-最后一段重击 |  |  |  | in progress |  |  | Char_Skill_C01_Focus_Atk1_5th
|  |  | 派生-蓄力攻击2-起手 | AN_Munin_TwinBlade_C_A_FocusAttack2 |  | 垂直击飞 | in progress | Skill_Munin_TwinBlade_FocusAttack2 | Char_Skill_C01_Focus_Atk2 | Char_Skill_C01_Focus_Atk2
|  |  | 派生-蓄力攻击2-2段 |  |  |  | in progress |  |  | Char_Skill_C01_Focus_Atk2_2nd
|  |  | 派生-蓄力攻击2-3段 |  |  |  | in progress |  |  | Char_Skill_C01_Focus_Atk2_3rd
|  |  | 派生-蓄力攻击2-4段 |  |  |  | in progress |  |  | Char_Skill_C01_Focus_Atk2_4th
|  |  | 派生-蓄力攻击2-5段 |  |  |  | in progress |  |  | Char_Skill_C01_Focus_Atk2_5th
|  |  | 派生-蓄力攻击2-6段 |  |  |  | in progress |  |  | Char_Skill_C01_Focus_Atk2_6th
|  |  | 派生-蓄力攻击2-最后一段重击 |  |  |  | in progress |  |  | Char_Skill_C01_Focus_Atk2_7th
|  |  | 派生-蓄力攻击2-结束 |  |  |  | in progress |  |  | Char_Skill_C01_Focus_Atk2_End
|  |  | 派生-蓄力攻击3-起手 | AN_Munin_TwinBlade_C_A_FocusAttack3 |  | 高输出以水平击飞结束，主要输出手段 | in progress | Skill_Munin_TwinBlade_FocusAttack3 | Char_Skill_C01_Focus_Atk3 | Char_Skill_C01_Focus_Atk3
|  |  | 派生-蓄力攻击3-2段 |  |  |  | in progress |  |  | Char_Skill_C01_Focus_Atk3_2nd
|  |  | 派生-蓄力攻击3-3段 |  |  |  | in progress |  |  | Char_Skill_C01_Focus_Atk3_3rd
|  |  | 派生-蓄力攻击3-4段 |  |  |  | in progress |  |  | Char_Skill_C01_Focus_Atk3_4th
|  |  | 派生-蓄力攻击3-5段 |  |  |  | in progress |  |  | Char_Skill_C01_Focus_Atk3_5th
|  |  | 派生-蓄力攻击3-6段 |  |  |  | in progress |  |  | Char_Skill_C01_Focus_Atk3_6th
|  |  | 派生-蓄力攻击3-7段 |  |  |  | in progress |  |  | Char_Skill_C01_Focus_Atk3_7th
|  |  | 派生-蓄力攻击3-8段 |  |  |  | in progress |  |  | Char_Skill_C01_Focus_Atk3_8th
|  |  | 派生-蓄力攻击3-9段 |  |  |  | in progress |  |  | Char_Skill_C01_Focus_Atk3_9th
|  |  | 派生-蓄力攻击3-10段 |  |  |  | in progress |  |  | Char_Skill_C01_Focus_Atk3_10th
|  |  | 派生-蓄力攻击3-最后一段重击 |  |  |  | in progress |  |  | Char_Skill_C01_Focus_Atk3_11th
|  | 副攻击 | 开火-单发 | AN_Munin_Revolver_C_P_FireOneShot | Munin_Strafe_Revolver |  | in progress | Skill_Munin_Revolver_FireOneShot | Char_Skill_C01_Strafe_Fire | Char_Skill_C01_Strafe_Fire
|  |  | 装填子弹开始 | AN_Munin_Revolver_C_P_ReloadBulltesSingle |  |  | in progress | Skill_Munin_Revolver_ReloadBulltesSingle | Char_Skill_C01_Strafe_Reload | Char_Skill_C01_Strafe_Reload_Start
|  |  | 装填子弹-单 | AN_Munin_Revolver_C_P_ReloadBulltesSingle |  |  | in progress | Skill_Munin_Revolver_ReloadBulltesSingle | Char_Skill_C01_Strafe_Reload | Char_Skill_C01_Strafe_Reload
|  |  | 举枪结束 | AN_Munin_Revolver_C_P_ExitStrafe |  |  | in progress | Skill_Munin_Revolver_ExitStrafe | Char_Skill_C01_Strafe_Exit | Char_Skill_C01_Strafe_Exit
|  |  | 收枪 |  |  |  | in progress |  |  | Char_Skill_C01_Strafe_End
|  |  | 切换武器 | AN_Munin_Revolver_C_P_ExitStrafe |  |  | in progress | Skill_Munin_Revolver_ExitStrafe | Char_Skill_C01_Strafe_Exit | Char_Skill_C01_Strafe_Switch
|  | 化解 | 化解-攻击 | AN_Munin_TwinBlade_C_A_StepCounter | Munin_StepCounter_B Munin_StepCounter_L Munin_StepCounter_R |  | in progress | Skill_Munin_TwinBlade_StepCounter | Char_Skill_C01_Counter | Char_Skill_C01_Counter | [7 empty] | 大招>化解、蓄力>挥刀
|  |  | 特殊化解-攻击 | AN_Munin_TwinBlade_C_A_StepSpecialCounter | Munin_StepCounter_Special |  | in progress | Skill_Munin_TwinBlade_StepSpecialCounter | Char_Skill_C01_Counter_Sp | Char_Skill_C01_Counter_Sp
|  | 中距离处决 | 地面冲刺Stand |  | Munin_Execution1_Stand Munin_Execution1_Air Munin_Execution2_Stand Munin_Execution2_Air |  | in progress |  |  | Char_Skill_C01_Execution1_Stand
|  |  | 钩锁释放Air |  |  |  | in progress |  |  | Char_Skill_C01_Execution1_Air
|  |  | 处决1技能 |  |  |  | in progress |  |  | Char_Skill_C01_Execution1
|  |  | 处决1收招 |  |  |  | in progress |  |  | Char_Skill_C01_Execution1_End
|  |  | 处决2技能 |  |  |  | in progress |  |  | Char_Skill_C01_Execution2
|  |  | 处决2收招 |  |  |  | in progress |  |  | Char_Skill_C01_Execution2_End
|  | 移动 | 一步内的基础垫步闪避 |  | Munin_Step |  | in progress |  |  | Char_Skill_C01_Dodge_Step
|  |  | 大位移的闪避动作，如翻滚（后向） | AN_Munin_TwinBlade_C_M_Dodge_B AN_Munin_TwinBlade_C_M_Dodge_F AN_Munin_TwinBlade_C_M_Dodge_L AN_Munin_TwinBlade_C_M_Dodge_R | Munin_Dodge |  | in progress | Skill_Munin_Dodge | Char_Skill_C01_Dodge | Char_Skill_C01_Dodge
|  | 切人 | 切人特效 |  | 策划GE配置 |  | in progress |  |  | Char_Other_Gen_Switch
|  | 大招 | 开始 | AN_Munin_TwinBlade_C_A_Ultimate_Start | Munin_Ultimate | 前段表演段，主要用于展现角色魅力 | in progress | Skill_Munin_TwinBlade_Ultimate | Char_Skill_C01_Ult | Char_Skill_C01_Ult
|  |  | 结束 | AN_Munin_TwinBlade_C_A_Ultimate_End |  | 大招砸地时产生重力场效果，液滴吸收后击飞敌人并使其失重 | in progress | Skill_Munin_TwinBlade_Ultimate_End | Char_Skill_C01_Ult_End | Char_Skill_C01_Ult_Smash
【角色】骑士：库拉蒂音效
Y1Q4 | C02女骑库拉蒂 | 普攻连段 | GratiaCombo1 | Gratia_Attack1 | Gratia_Attack1 |  | in progress | Skill_Gratia_Attack1 | Char_Skill_C1502_Atk1 | Char_Skill_C02_Atk1 |  | 大剑的普攻不能轻盈，攻击whoosh需体现力量感，挥舞伴有金属刀光和有威胁力的风声，但同时也不要显得过于笨重
|  |  | GratiaCombo1收招 |  |  |  | in progress |  | Char_Skill_C1502_Atk1_End | Char_Skill_C02_Atk1_End
|  |  | GratiaCombo2 | Gratia_Attack2 | Gratia_Attack2 |  | in progress | Skill_Gratia_Attack2 | Char_Skill_C1502_Atk2 | Char_Skill_C02_Atk2 | [7 empty] | 第二击2段有地面剑痕是不是可以加一点效果
|  |  | GratiaCombo2第二段 |  |  |  | in progress |  |  | Char_Skill_C02_Atk2_2nd
|  |  | GratiaCombo2收招 |  |  |  | in progress |  | Char_Skill_C1502_Atk2_End | Char_Skill_C02_Atk2_End
|  |  | GratiaCombo3 | Gratia_Attack3 | Gratia_Attack3 |  | in progress | Skill_Gratia_Attack3 | Char_Skill_C1502_Atk3 | Char_Skill_C02_Atk3
|  |  | GratiaCombo3收招 |  |  |  | in progress |  | Char_Skill_C1502_Atk3_End | Char_Skill_C02_Atk3_End
|  |  | GratiaCombo4 | Gratia_Attack4 | Gratia_Attack4 | 挑飞 | in progress | Skill_Gratia_Attack4 | Char_Skill_C1502_Atk4 | Char_Skill_C02_Atk4 | [7 empty] | 和第二段同理
|  |  | GratiaCombo4收招 |  |  |  | in progress |  | Char_Skill_C1502_Atk4_End | Char_Skill_C02_Atk4_End
|  |  | GratiaCombo5 | Gratia_Attack5 | Gratia_Attack5 | 跳起砸地，击倒 | in progress | Skill_Gratia_Attack5 | Char_Skill_C1502_Atk5 | Char_Skill_C02_Atk5
|  |  | GratiaCombo5第二段跳起 |  |  |  | in progress |  |  | Char_Skill_C02_Atk5_2nd
|  |  | GratiaCombo5第三段砸地 |  |  |  | in progress |  |  | Char_Skill_C02_Atk5_3rd
|  |  | GratiaCombo5收招 |  |  |  | in progress |  | Char_Skill_C1502_Atk5_End | Char_Skill_C02_Atk5_End
|  | 盾牌派生攻击 | GratiaComboDodge闪避普攻 |  | Gratia_RushAttack |  | in progress |  |  | Char_Skill_C02_Atk_Rush
|  |  | 盾击一派生攻击1 | Gratia_ShieldAtk2 | Gratia_ShieldAttack2 |  | in progress | Skill_Gratia_Shiled_DefenseCounterAtk2 | Char_Skill_C1502_Strafe_Counter_Atk1 | Char_Skill_C02_Strafe_Counter_Atk1
|  |  | 盾击一派生攻击2 | Gratia_ShieldAtk3 | Gratia_ShieldAttack3 |  | in progress | Skill_Gratia_Shiled_DefenseCounterAtk3 | Char_Skill_C1502_Strafe_Counter_Atk2 | Char_Skill_C02_Strafe_Counter_Atk2
|  |  | 盾击一派生攻击2二段 |  |  |  | in progress |  |  | Char_Skill_C02_Strafe_Counter_Atk2_2nd
|  | 蓄力攻击 | 普攻连段派生-蓄力前摇 | Gratia_FocusReady1 | Gratia_Focus_FromReady1 | 吸收周围液滴附着在大剑上 | in progress | Skill_Gratia_FocusReady1 | Char_Skill_C1502_Focus_Ready1 | Char_Skill_C02_Focus_Ready1 |  | 强调大剑的体积和力量感，吸收白银液滴的过程不能是轻薄的水声，液体质地需要体现厚重感和金属特质
|  |  | 派生-蓄力攻击1阶段1 | Gratia_FocusAttack1 | Gratia_FocusAttack1 | 砸地 | in progress | Skill_Gratia_FocusAttack1 | Char_Skill_C1502_Focus_Atk1 | Char_Skill_C02_Focus_Atk1 |  | 对比普攻，加强下劈的力度和威胁性，更加突出沉重金属刀光
|  |  | 派生-蓄力攻击1阶段2 |  |  |  | in progress |  |  | Char_Skill_C02_Focus_Atk1_2nd
|  |  | 派生-蓄力攻击2阶段1 | Gratia_FocusAttack2 | Gratia_FocusAttack2 | 抡剑旋转，击退敌人 | in progress | Skill_Gratia_FocusAttack2 | Char_Skill_C1502_Focus_Atk2 | Char_Skill_C02_Focus_Atk2 |  | 抡剑产生喷溅的金属液滴并造成击退效果
|  |  | 派生-蓄力攻击2阶段2 |  |  |  | in progress |  | Char_Skill_C1502_Focus_Atk2_2nd | Char_Skill_C02_Focus_Atk2_2nd
|  |  | 派生-蓄力攻击2阶段3 |  |  |  | in progress |  |  | Char_Skill_C02_Focus_Atk2_3rd
|  |  | 派生-蓄力攻击2阶段4 |  |  |  | in progress |  |  | Char_Skill_C02_Focus_Atk2_4th
|  |  | 派生-蓄力攻击2阶段5 |  |  |  | in progress |  |  | Char_Skill_C02_Focus_Atk2_5th
|  |  | 派生-蓄力攻击3起手阶段1 | Gratia_FocusAttack3 | Gratia_FocusAttack3 | 抡剑大风车衔接蓄力前摇的前面两周 | in progress | Skill_Gratia_FocusAttack3 | Char_Skill_C1502_Focus_Atk3_Start | Char_Skill_C02_Focus_Atk3_Start
|  |  | 派生-蓄力攻击3起手阶段2 |  |  | 抡剑大风车后面三周，最后一周衔接下一招上挑 | in progress |  | Char_Skill_C1502_Focus_Atk3_Start_2nd | Char_Skill_C02_Focus_Atk3_Start_2nd
|  |  | 派生-蓄力攻击3起手阶段3 |  |  |  | in progress |  |  | Char_Skill_C02_Focus_Atk3_Start_3rd
|  |  | 派生-蓄力攻击3阶段3跳起 |  |  |  | in progress |  |  | Char_Skill_C02_Focus_Atk3
|  |  | 派生-蓄力攻击3阶段3二段 |  |  |  | in progress |  |  | Char_Skill_C02_Focus_Atk3_2nd
|  |  | 蓄力攻击通用end |  |  | 蓄力攻击结束后收刀回到原位 | in progress |  | Char_Skill_C1502_Focus_Atk_End | Char_Skill_C02_Focus_Atk_End
|  | 副攻击-举盾格挡 | 进入举盾strafe | Gratia_ShieldDefenseStart | Gratia_Strafe_Shield | 前格挡开始 | in progress | Skill_Gratia_Shiled_EnterStrafe | Char_Skill_C1502_Strafe_Enter | Char_Skill_C02_Strafe_Enter |  | 表现持盾破开空气的冲击和盾的金属重量感
|  |  | 退出举盾strafe | Gratia_ShieldExitStrafe |  | 前格挡结束 盾化解变回大剑 | in progress | Skill_Gratia_Shiled_ExitStrafe | Char_Skill_C1502_Strafe_Exit | Char_Skill_C02_Strafe_Exit
|  |  | 盾击 | Gratia_Strafe_Shield |  | 举盾前冲并大幅击飞敌人 | in progress | Skill_Gratia_Shiled_DefenseRebound | Char_Skill_C1502_Strafe_Defense_Atk | Char_Skill_C02_Strafe_Defense_Atk |  | 厚重钝击，呈现重量但不需锋利感，避免使用slash刀光声，有冲击感
|  |  | 前格挡受击 | Gratia_ShieldDefenseHit |  |  | in progress | Skill_Gratia_Shiled_DefenseHit | Char_Skill_C1502_Strafe_Defense_Hit | Char_Skill_C02_Strafe_Defense_Hit | [7 empty] | 没听到声音
|  |  | 前格挡破防 | Gratia_DefenseBreak | Gratia_DefenseBreak | 盾受击碎裂消散 | in progress | Skill_Gratia_Shiled_DefenseBreak | Char_Skill_C1502_Strafe_Defense_Break | Char_Skill_C02_Strafe_Defense_Break
|  | 闪避 | 一步内的虚晃闪避动作（一段闪避） | Gratia_Step | Gratia_Step |  | in progress |  | Char_Skill_C1502_Dodge_Step | Char_Skill_C02_Dodge_Step |  | 动作要迅速，音效不能拖沓和过重，除cloth foley外可以伴有明显的盔甲撞击声
|  |  | 大位移的闪避动作（二段闪避） | Gratia_Dodge | Gratia_Dodge | 翻滚，而后落地站起 | in progress | Skill_Gratia_Dodge | Char_Skill_C1502_Dodge | Char_Skill_C02_Dodge
|  | 化解 | 轻化解 | Gratia_StepCounter_B Gratia_StepCounter_L Gratia_StepCounter_R | Gratia_StepCounter_B Gratia_StepCounter_L Gratia_StepCounter_R | 快速举盾进行前向格挡，并向后闪避 | in progress | Skill_Gratia_StepCounter | Char_Skill_C1502_Counter | Char_Skill_C02_Counter |  | 体现出与闪避音效不同的坚定感，foley动作少而突出盾的存在感，不需要轻飘飘
|  |  | 特殊化解 | Gratia_StepCounter_Special | Gratia_StepCounter_Special | 快速举盾向前格挡，并大幅后撤拉开距离 | in progress | Skill_Gratia_StepSpecialCounter_B | Char_Skill_C1502_Counter_Sp_Atk | Char_Skill_C02_Counter_Sp_Atk
|  | 处决 | 通用/特殊处决开始衔接-近距离地面 | Gratia_Execution1_Stand_Far | Gratia_Execution1_Stand_Far |  | in progress | Skill_Gratia_Execution1_Pre_Far | Char_Skill_C1502_Execu1_Pre_Far | Char_Skill_C02_Execu1_Pre_Far
|  |  | 通用/特殊处决开始衔接-近距离空中钩锁 | Gratia_Execution1_Air_Close | Gratia_Execution1_Air_Close |  | in progress | Skill_Gratia_Execution1_Pre_Hook | Char_Skill_C1502_Execu1_Pre_Hook | Char_Skill_C02_Execu1_Pre_Hook
|  |  | 通用/特殊处决开始衔接-远距离空中钩锁 | Gratia_Execution1_Air_Far | Gratia_Execution1_Air_Far |  | in progress | Skill_Gratia_Execution1_Pre_Far_Hook | Char_Skill_C1502_Execu1_Pre_Far_Hook | Char_Skill_C02_Execu1_Pre_Far_Hook
|  |  | 处决1-收招 |  |  |  | in progress |  |  | Char_Skill_C02_Execu1_End
|  |  | 处决1-通用处决 | Gratia_Execution1_Stand | Gratia_Execution1_Stand |  | in progress | Skill_Gratia_Execution1 | Char_Skill_C1502_Execu1 | Char_Skill_C02_Execu1
|  | 特殊处决 | 处决2-特殊处决开始 | Gratia_Execution2_Stand | Gratia_Execution2_Stand |  | in progress | Skill_Gratia_Execution2_Start | Char_Skill_C1502_Execu2_Start | Char_Skill_C02_Execu2_Start
|  |  | 处决2-特殊处决跑循环 |  |  |  | in progress | Skill_Gratia_Execution2_Loop | Char_Skill_C1502_Execu2_LP | Char_Skill_C02_Execu2_LP
|  |  | 处决2-特殊处决结束 |  |  |  | in progress | Skill_Gratia_Execution2_End | Char_Skill_C1502_Execu2_End | Char_Skill_C02_Execu2_End
|  |  | 处决2-特殊处决撞墙结束 |  |  |  | in progress | Skill_Gratia_Execution2_End_SP | Char_Skill_C1502_Execu2_End_Sp | Char_Skill_C02_Execu2_End_Sp
|  | 大招 | 大招起手 | Gratia_Ultmate | Gratia_Ultmate | 大剑和全身的白银装甲液化，汇聚于右手积蓄能量，液银形成冰冻长矛。长矛经过远距离投掷，击中目标爆炸，造成击飞和冻结的巨大伤害 | in progress | Skill_Gratia_Skill2 | Char_Skill_C1502_Ult | Char_Skill_C02_Ult |  | 液银汇聚的过程与蓄力攻击前摇类似，但威力要更强，长矛投出需体现冰冻属性及本身的重量，飞行过程中有破空的冲击速度，附带冰霜拖尾，整体要强调出大招的华丽度
|  |  | 大招释放 |  |  |  | in progress |  |  | Char_Skill_C02_Ult_2nd
|  |  | 长矛击穿单位并插入墙面（GE配置） | Gratia_Spear_Explosion_Wall |  |  | in progress |  | Char_Skill_C1502_Ult_End | Char_Skill_C02_Ult_End
|  |  | 长矛碎裂爆炸回复铠甲（GE配置） | Gratia_Spear_Explosion_Air |  | 冰冻长矛爆炸 | in progress |  | Char_Skill_C1502_Ult_Exp | Char_Skill_C02_Ult_Exp | [7 empty] | 音效表现不对
射击和燃烧角色
Y1Q4 | C07法医法索 | 普攻连段 | 1段 |  | Firtho_Attack1 |  | in progress |  |  | Char_Skill_C07_Atk1
|  |  | 1段收招 |  |  |  | in progress |  |  | Char_Skill_C07_Atk1_End
|  |  | 2段挥砍1 |  | Firtho_Attack2 |  | in progress |  |  | Char_Skill_C07_Atk2
|  |  | 2段挥砍2 |  |  |  | in progress |  |  | Char_Skill_C07_Atk2_2nd
|  |  | 2段收招 |  |  |  | in progress |  |  | Char_Skill_C07_Atk2_End
|  |  | 3段 |  | Firtho_Attack3 |  | in progress |  |  | Char_Skill_C07_Atk3
|  |  | 3段收招 |  |  |  | in progress |  |  | Char_Skill_C07_Atk3_End
|  |  | 4段起手 |  | Firtho_Attack4 |  | in progress |  |  | Char_Skill_C07_Atk4
|  |  | 4段跳起 |  |  |  | in progress |  |  | Char_Skill_C07_Atk4_2nd
|  |  | 4段砸地 |  |  |  | in progress |  |  | Char_Skill_C07_Atk4_3rd
|  |  | 4段收招 |  |  |  | in progress |  |  | Char_Skill_C07_Atk4_End
|  | 特殊普攻 | 冲刺普攻 |  | Firtho_RushAttack |  | in progress |  |  | Char_Skill_C07_Atk_Rush
|  |  | 冲刺普攻收招 |  |  |  | in progress |  |  | Char_Skill_C07_Atk_Rush_End
|  | 副攻击 | 起手 |  | Firtho_Q4Strafe |  | in progress |  |  | Char_Skill_C07_Strafe_Start
|  |  | 1级挥砍 |  |  |  | in progress |  |  | Char_Skill_C07_Strafe_Hack1
|  |  | 1级挥砍收招 |  |  |  | in progress |  |  | Char_Skill_C07_Strafe_End1
|  |  | 2级格挡 |  |  |  | in progress |  |  | Char_Skill_C07_Strafe_Block
|  |  | 2级挥砍 |  |  |  | in progress |  |  | Char_Skill_C07_Strafe_Hack2
|  |  | 2级挥砍收招 |  |  |  | in progress |  |  | Char_Skill_C07_Strafe_End2
|  | 蓄力攻击 | 前摇 |  | Firtho_FocusReady1 |  | in progress |  |  | Char_Skill_C07_Focus_Ready
|  |  | 蓄力1级 |  |  |  | in progress |  |  | Char_Skill_C07_Focus1
|  |  | 蓄力2级 |  |  |  | in progress |  |  | Char_Skill_C07_Focus2
|  | 闪避 | 一段闪避 |  | Firtho_Step |  | in progress |  |  | Char_Skill_C07_Dodge_Step
|  |  | 二段闪避 |  | Firtho_Dodge |  | in progress |  |  | Char_Skill_C07_Dodge
|  | 化解 | 轻化解 |  | Firtho_StepCounter_B/L/R |  | in progress |  |  | Char_Skill_C07_Counter
|  |  | 重化解 |  | Firtho_StepCounter_Special |  | in progress |  |  | Char_Skill_C07_Counter_Sp
|  | 处决 | 处决-空中 |  | Firtho_Execution1_Air/Firtho_Execution2_Air |  | in progress |  |  | Char_Skill_C07_Execu1_Air
|  |  | 通用处决释放 |  | Firtho_Execution1_Air/Firtho_Execution1_Stand |  | in progress |  |  | Char_Skill_C07_Execu1
|  |  | 通用处决收招 |  |  |  | in progress |  |  | Char_Skill_C07_Execu1_End
|  |  | 特殊处决释放 |  | Firtho_Execution2_Air/Firtho_Execution2_Stand |  | in progress |  |  | Char_Skill_C07_Execu2
|  |  | 特殊处决收招 |  |  |  | in progress |  |  | Char_Skill_C07_Execu2_End
|  | 大招 | 表演Sequence |  | Firtho_Ultimate |  | in progress |  |  | Char_Skill_C07_Ult
|  |  | 释放砸地 |  |  |  | in progress |  |  | Char_Skill_C07_Ult_Smash
|  |  | 收招 |  |  |  | in progress |  |  | Char_Skill_C07_Ult_End
射击和燃烧角色
Y1Q4 | C08灰姑娘厄什栗 | 普攻连段 | 普攻1 |  | Attack1 |  | in progress |  |  | Char_Skill_C08_Atk1
|  |  | 普攻2-第1段 |  |  |  | in progress |  |  | Char_Skill_C08_Atk2
|  |  | 普攻2-第2段 |  | Attack2 |  | in progress |  |  | Char_Skill_C08_Atk2_2nd
|  |  | 普攻3 |  | Attack3 |  | in progress |  |  | Char_Skill_C08_Atk3
|  |  | 普攻4 |  | Attack4 |  | in progress |  |  | Char_Skill_C08_Atk4
|  |  | 普攻5-第1段跳起 |  | Attack5 |  | in progress |  |  | Char_Skill_C08_Atk5
|  |  | 普攻5-第2段砸地 |  |  |  | in progress |  |  | Char_Skill_C08_Atk5_2nd
|  |  | 普攻5-收招 |  |  |  | in progress |  |  | Char_Skill_C08_Atk5_End
|  | 特殊普攻 | 冲刺普攻 |  | RushAttack |  | in progress |  |  | Char_Skill_C08_Atk_Rush
|  |  | 爆发普攻1 |  | FlareAttack1 |  | in progress |  |  | Char_Skill_C08_FlareAtk1
|  |  | 爆发普攻2-第1段跳起 |  | FlareAttack2 |  | in progress |  |  | Char_Skill_C08_FlareAtk2
|  |  | 爆发普攻2-第2段释放 |  |  |  | in progress |  |  | Char_Skill_C08_FlareAtk2_2nd
|  |  | 爆发普攻3-第1段跳起 |  | FlareAttack3 |  | in progress |  |  | Char_Skill_C08_FlareAtk3
|  |  | 爆发普攻3-第2段蓄力 |  |  |  | in progress |  |  | Char_Skill_C08_FlareAtk3_2nd
|  |  | 爆发普攻3-第3段跳砸 |  |  |  | in progress |  |  | Char_Skill_C08_FlareAtk3_3rd
|  | 普通蓄力攻击 | 普通蓄力前摇 |  | FocusReady_Normal |  | in progress |  |  | Char_Skill_C08_Focus_N_Ready
|  |  | 蓄力释放等级1 |  |  |  | in progress |  |  | Char_Skill_C08_Focus_N_Lv1
|  |  | 蓄力释放等级2 |  |  |  | in progress |  |  | Char_Skill_C08_Focus_N_Lv2
|  |  | 蓄力释放等级2-第二段 |  |  |  | in progress |  |  | Char_Skill_C08_Focus_N_Lv2_2nd
|  |  | 蓄力释放等级3 |  |  |  | in progress |  |  | Char_Skill_C08_Focus_N_Lv3
|  |  | 蓄力释放等级3-第二段 |  |  |  | in progress |  |  | Char_Skill_C08_Focus_N_Lv3_2nd
|  | 燃烧模式蓄力攻击 | 燃烧模式蓄力前摇 |  | FocusReady_FlareMode |  | in progress |  |  | Char_Skill_C08_Focus_F_Ready
|  |  | 蓄力释放等级1 |  |  |  | in progress |  |  | Char_Skill_C08_Focus_F_Lv1
|  |  | 蓄力释放等级2 |  |  |  | in progress |  |  | Char_Skill_C08_Focus_F_Lv2
|  |  | 蓄力释放等级2-第二段 |  |  |  | in progress |  |  | Char_Skill_C08_Focus_F_Lv2_2nd
|  |  | 蓄力释放等级3 |  |  |  | in progress |  |  | Char_Skill_C08_Focus_F_Lv3
|  |  | 蓄力释放等级3-第二段 |  |  |  | in progress |  |  | Char_Skill_C08_Focus_F_Lv3_2nd
|  | 射击技能 | 起手 |  | Strafe_MachineGun_Normal |  | in progress |  |  | Char_Skill_C08_Strafe_Start
|  |  | 机枪抬起 |  |  |  | in progress |  |  | Char_Skill_C08_Strafe_Fill
|  |  | 换弹 |  |  |  | in progress |  |  | Char_Skill_C08_Strafe_Reload
|  |  | 结束 |  |  |  | in progress |  |  | Char_Skill_C08_Strafe_End
|  |  | 普通机枪 |  |  |  | in progress |  |  | Char_Skill_C08_Strafe_Shoot
|  |  | 燃烧模式机枪 |  | Strafe_MachineGun_FlareMode |  | in progress |  |  | Char_Skill_C08_Strafe_F_Shoot
|  |  | 爆发射击 |  | Strafe_MaxRotateSpeedBurst_FlareMode |  | in progress |  |  | Char_Skill_C08_Strafe_Max
|  | 闪避 | 一段闪避 |  | Step |  | in progress |  |  | Char_Skill_C08_Dodge_Step
|  |  | 二段闪避 |  | Dodge |  | in progress |  |  | Char_Skill_C08_Dodge
|  | 化解 | 轻化解 |  | StepCounter |  | in progress |  |  | Char_Skill_C08_Counter
|  |  | 重化解 |  | StepCounter_Special |  | in progress |  |  | Char_Skill_C08_Counter_Sp
|  | 处决 | 处决-空中 |  | Execution1_Air |  | in progress |  |  | Char_Skill_C08_Execu1_Air
|  |  | 处决1-释放 |  | Execution1_Air/Execution1_Stand |  | in progress |  |  | Char_Skill_C08_Execu1
|  |  | 处决2-释放 |  | Execution2_Air/Execution2_Stand |  | in progress |  |  | Char_Skill_C08_Execu2
|  | 大招 | 大招释放 |  | Ultimate |  | in progress |  |  | Char_Skill_C08_Ult
|  |  | 大招释放的导弹爆破 |  | 需要策划GE配置 |  | in progress |  |  | Char_Skill_C08_Ult_Explode
射击和燃烧角色

## Boss
需求版本 | 需求模块 Require Module | 二级模块 Second Module | 需求名 Require Name | *音频配置位置（技能编辑器） | 需求描述 Skill Description | 音频状态 Status | 音效名（旧） | 音效名 Sample Name | 参考视频名称 Video | 音效描述 Sound event Description | 音频交付时间 Due Time | 样本数量 Sample Number | 技能播放方式 One shot/Loop | 声音绑定方式 Sound Binding Method | 备注 Remarks | 样本问题及优化方向 V1 | 补充 V1 | 样本问题及优化方向 V2 | 补充 V2 | 样本问题及优化方向 V3 | 补充 V3 | 样本问题及优化方向 V4 | 补充 V4 | 样本问题及优化方向 V5 | 补充 V5
Boss_Skill_Boss名称_技能名称_状态
Y1Q4 | B01灰姑娘Boss | 马车大回环 | 甩尾前的车厢动画音效 |  |  | in progress |  | Mon_Boss_Part_B01_Drift_Pre
|  |  | 甩尾前的车厢火焰喷射音效 |  |  | in progress |  | Mon_Boss_Part_B01_Drift_Fire
|  |  | 大回环启动时的火焰喷射音效，左右通用 | BossAshley_CarriageDrift_Left BossAshley_CarriageDrift_Right |  | in progress | Boss_Ashley_Skill_Carriage_Drift | Mon_Boss_Part_B01_Drift
|  |  | 甩尾音效 |  |  | in progress |  | Mon_Boss_Part_B01_Drift_2nd
|  |  | 甩尾结束后的马车着地声 |  |  | in progress |  | Mon_Boss_Part_B01_Drift_End
|  | 驻场南瓜车combo2大回环 | state1，左右通用 | BossAshley_Combo2_DriftL BossAshley_Combo2_DriftR |  | cancel | Boss_Ashley_Skill_Combo_Drift | Mon_Boss_Part_B01_Combo_Drift
|  | 马车冲撞-积极等级1 | state1，起手动作，等级1和2通用 | BossAshley_ChargeStorage_Lv1 |  | in progress | Boss_Ashley_Skill_Charge_Storage_Start1 | Mon_Boss_Part_B01_Charge_Pre
|  |  | state1，起手动作点火声 |  |  | in progress |  | Mon_Boss_Part_B01_Charge_Fire
|  |  | state2，等级1和2通用 |  |  | in progress | Boss_Ashley_Skill_Charge_Storage_Start2 | Mon_Boss_Part_B01_Charge_Start
|  |  | state2，马车喷火，等级1和2通用 |  |  | in progress | Boss_Ashley_Skill_Charge_Storage_Boom | Mon_Boss_Part_B01_Charge_Boom
|  |  | state3，马车向前冲刺的过程 |  |  | cancel | Boss_Ashley_Skill_Charge_Storage_Move_Lv1 | Mon_Boss_Part_B01_Charge_Move_Lv1
|  |  | state4，结束动作，等级1和2通用 |  |  | in progress | Boss_Ashley_Skill_Charge_Storage_End | Mon_Boss_Part_B01_Charge_End
|  | 马车冲撞-积极等级2 | state3，马车向前冲刺的过程 | BossAshley_ChargeStorage_Lv2 |  | in progress | Boss_Ashley_Skill_Charge_Storage_Move_Lv2 | Mon_Boss_Part_B01_Charge_Move_Lv2
|  | 驻场冲撞-积极等级1 | state2 | BossAshley_ResidentCharge_Lv1 |  | in progress | Boss_Ashley_Skill_Resident_Charge_Start_Lv1 | Mon_Boss_Part_B01_Resident_Charge_Start_Lv1
|  |  | state4 |  |  | in progress | Boss_Ashley_Skill_Resident_Charge_End_Lv1 | Mon_Boss_Part_B01_Resident_Charge_End_Lv1
|  | 驻场冲撞-积极等级2 | state2 | BossAshley_ResidentCharge_Lv2 |  | in progress | Boss_Ashley_Skill_Resident_Charge_Start_Lv2 | Mon_Boss_Part_B01_Resident_Charge_Start_Lv2
|  |  | state4 |  |  | in progress | Boss_Ashley_Skill_Resident_Charge_End_Lv2 | Mon_Boss_Part_B01_Resident_Charge_End_Lv2
|  | FarawayFromChar | 马车向前冲刺的过程 |  |  | in progress |  | Mon_Boss_Part_B01_Far_Move
|  | MoveSlow | 马车缓慢逼近 |  |  | in progress |  | Mon_Boss_Part_B01_Moveslow
|  | 一阶段蜘蛛雷 | 蜘蛛雷爆破 | BossAshley_SpiderMine（需要策划配置） |  | in progress | Boss_Ashley_Skill_Spider_Mine_Explode | Mon_Boss_Part_B01_Spider_Mine_Explode
|  |  | 蜘蛛雷移动 |  |  | in progress |  | Mon_Boss_Part_B01_Spider_Mine_Run
|  |  | 蜘蛛雷死亡 |  |  | in progress |  | Mon_Boss_Part_B01_Spider_Mine_Death
|  | 南瓜派对-积极等级1 | 南瓜车导弹发射 | BossAshley_PumpkinParty_Lv1（需要策划配置） |  | in progress | Boss_Ashley_Skill_Party_Missile_Launch | Mon_Boss_Part_B01_Party_Missile_Launch
|  |  | 南瓜车车厢细节音效 |  |  | in progress |  | Mon_Boss_Part_B01_Party_Pre
|  |  | 导弹发射的拖尾声 |  |  | in progress | Boss_Ashley_Skill_Party_Missile_Tail | Mon_Boss_Part_B01_Party_Missile_Tail
|  |  | 导弹爆破声 |  |  | in progress | Boss_Ashley_Skill_Party_Missile_Boom | Mon_Boss_Part_B01_Party_Missile_Boom
|  |  | 马匹受惊的嘶吼 |  |  | in progress |  | Mon_Boss_Part_B01_Party_Voice
|  |  | 马匹受惊的蹬地 |  |  | in progress |  | Mon_Boss_Part_B01_Party_Land
|  | 南瓜种子-积极等级1 | state1动画音效 | BossAshley_PumpkinSeed_Lv1（需要策划配置） |  | in progress | Boss_Ashley_Skill_Seed_Start_Lv1 | Mon_Boss_Part_B01_Seed_Start_Lv1
|  |  | 导弹发射 |  |  | in progress | Boss_Ashley_Skill_Seed_Launch | Mon_Boss_Part_B01_Seed_Missile_Launch
|  |  | 导弹爆破声 |  |  | in progress | Boss_Ashley_Skill_Seed_Missile_Boom | Mon_Boss_Part_B01_Seed_Missile_Boom
|  | 南瓜种子-积极等级2 | state1动画音效 | BossAshley_PumpkinSeed_Lv2 |  | in progress | Boss_Ashley_Skill_Seed_Start_Lv2 | Mon_Boss_Part_B01_Seed_Start_Lv2
|  | 火焰手风琴-积极等级1 | 火焰喷射第1段 | BossAshley_FlameAccordion_Lv1 |  | in progress | Boss_Ashley_Skill_Flame_Accordion_Lv1 | Mon_Boss_Part_B01_Flame_Accordion_Lv1
|  |  | 火焰喷射第2段 |  |  | in progress |  | Mon_Boss_Part_B01_Flame_Accordion_Lv1_2nd
|  | 火焰手风琴-积极等级2 | 火焰喷射第1段 | BossAshley_FlameAccordion_Lv2 |  | in progress | Boss_Ashley_Skill_Flame_Accordion_Lv2 | Mon_Boss_Part_B01_Flame_Accordion_Lv2
|  |  | 火焰喷射第2段 |  |  | in progress |  | Mon_Boss_Part_B01_Flame_Accordion_Lv2_2nd
|  |  | 火焰喷射第3段 |  |  | in progress |  | Mon_Boss_Part_B01_Flame_Accordion_Lv2_3rd
|  | 战争践踏-积极等级1 | state1 | BossAshley_Trample_Lv1 |  | in progress | Boss_Ashley_Skill_Trample_Start | Mon_Boss_Part_B01_Trample_Start
|  |  | state2 |  |  | in progress | Boss_Ashley_Skill_Trample_Smash | Mon_Boss_Part_B01_Trample_End
|  | 战争践踏-积极等级2 | 马慢速移动的脚步声 |  |  | in progress |  | Mon_Boss_Part_B01_Walk
|  | 驻场南瓜车向目标跑 | state1起手 | BossAshley_Move |  | in progress | Boss_Ashley_Skill_Move_Start | Mon_Boss_Part_B01_Move_Pre
|  |  | 马车向前冲刺 |  |  | in progress | Boss_Ashley_Skill_Move | Mon_Boss_Part_B01_Move
|  | 马车跳劈 | 动画起手火焰喷射 | BossAshley_CarriageBombing |  | in progress | Boss_Ashley_Skill_Carriage_Bombing_Start | Mon_Boss_Part_B01_Bombing_Start
|  |  | 马车腾空 |  |  | in progress | Boss_Ashley_Skill_Carriage_Bombing_Jump | Mon_Boss_Part_B01_Bombing_Jump
|  |  | 下落砸地 |  |  | in progress | Boss_Ashley_Skill_Carriage_Bombing_Smash | Mon_Boss_Part_B01_Bombing_End
|  | 灰姑娘跳下马车 | 跳起 | BossAshley_JumpToGround |  | in progress | Boss_Ashley_Skill_Jump | Mon_Boss_Part_B01_Jump_Start
|  |  | 砸地 |  |  | in progress | Boss_Ashley_Skill_Jump_Smash | Mon_Boss_Part_B01_Jump_End
|  | AshleyCombo1 | 普攻1第一段 | BossAshley_Attack1 |  | in progress | Boss_Ashley_Skill_Combo1 | Mon_Boss_Body_B01_Combo1
|  |  | 普攻1第二段 |  |  | in progress |  | Mon_Boss_Body_B01_Combo1_2nd
|  | AshleyCombo2 | 普攻2第一段 | BossAshley_Attack2 |  | in progress | Boss_Ashley_Skill_Combo2 | Mon_Boss_Body_B01_Combo2
|  |  | 普攻2第二段 |  |  | in progress |  | Mon_Boss_Body_B01_Combo2_2nd
|  | AshleyCombo3 | 普攻3 | BossAshley_Attack3_Start |  | in progress | Boss_Ashley_Skill_Combo3 | Mon_Boss_Body_B01_Combo3
|  | AshleyCombo4 | 普攻4第一段 | BossAshley_Attack4 |  | in progress | Boss_Ashley_Skill_Combo4 | Mon_Boss_Body_B01_Combo4
|  |  | 普攻4第二段 |  |  | in progress |  | Mon_Boss_Body_B01_Combo4_2nd
|  | AshleyCombo5 | 普攻5一段 | BossAshley_Attack5 |  | in progress | Boss_Ashley_Skill_Combo5_Part1 | Mon_Boss_Body_B01_Combo5
|  |  | 普攻5二段 |  |  | in progress | Boss_Ashley_Skill_Combo5_Part2 | Mon_Boss_Body_B01_Combo5_2nd
|  |  | 普攻5三段 |  |  | in progress | Boss_Ashley_Skill_Combo5_Part3 | Mon_Boss_Body_B01_Combo5_3rd
|  |  | 普攻5四段 |  |  | in progress |  | Mon_Boss_Body_B01_Combo5_4th
|  |  | 普攻5五段 |  |  | in progress |  | Mon_Boss_Body_B01_Combo5_5th
|  |  | 普攻5六段 |  |  | in progress |  | Mon_Boss_Body_B01_Combo5_6th
|  |  | 普攻5七段 |  |  | in progress |  | Mon_Boss_Body_B01_Combo5_7th
|  | Ashley_Fire | 机关枪单次射击音效 | BossAshley_AshleyShotGun（需要策划配置） |  | in progress | Boss_Ashley_Skill_Shoot_Single | Mon_Boss_Body_B01_Shoot
|  | Ashley后撤 | 闪避 | BossAshley_Dodge |  | in progress | Boss_Ashley_Skill_Dodge | Mon_Boss_Body_B01_Dodge
|  | AshleyCrystalShoes | 踢腿攻击 | BossAshley_CrystalShoes |  | in progress | Boss_Ashley_Skill_Crystalshoes | Mon_Boss_Body_B01_Kick_Atk
|  | AshleyKnightKick | 移动 | BossAshley_KnightKick |  | in progress | Boss_Ashley_Skill_Knightkick_Step | Mon_Boss_Body_B01_Kick_Step
|  |  | 踢腿砸地 |  |  | in progress | Boss_Ashley_Skill_Knightkick | Mon_Boss_Body_B01_Kick
|  | AshleyExecutePre | 火焰爆破 | BossAshley_ExecutionPre |  | in progress | Boss_Ashley_Skill_Execution_Pre | Mon_Boss_Body_B01_Execu_Pre
|  | AshleyExecute | state1第一段 | BossAshley_Execution |  | in progress | Boss_Ashley_Skill_Execution_State1 | Mon_Boss_Body_B01_Execu_State1
|  |  | state1第二段 |  |  | in progress |  | Mon_Boss_Body_B01_Execu_State1_2nd
|  |  | state1第三段 |  |  | in progress |  | Mon_Boss_Body_B01_Execu_State1_3rd
|  |  | state1第四段 |  |  | in progress |  | Mon_Boss_Body_B01_Execu_State1_4th
|  |  | state2第一段 |  |  | in progress | Boss_Ashley_Skill_Execution_State2 | Mon_Boss_Body_B01_Execu_State2
|  |  | state2第二段 |  |  | in progress |  | Mon_Boss_Body_B01_Execu_State2_2nd
|  |  | state2第三段 |  |  | in progress |  | Mon_Boss_Body_B01_Execu_State2_3rd
|  |  | state2第四段 |  |  | in progress |  | Mon_Boss_Body_B01_Execu_State2_4th
|  |  | state2第五段 |  |  | in progress |  | Mon_Boss_Body_B01_Execu_State2_5th
|  |  | state3第一段 |  |  | in progress | Boss_Ashley_Skill_Execution_State3 | Mon_Boss_Body_B01_Execu_State3
|  |  | state3第二段 |  |  | in progress |  | Mon_Boss_Body_B01_Execu_State3_2nd
|  |  | state4第一段 |  |  | in progress | Boss_Ashley_Skill_Execution_State4 | Mon_Boss_Body_B01_Execu_State4
|  |  | state4第二段 |  |  | in progress |  | Mon_Boss_Body_B01_Execu_State4_2nd
|  |  | state5 |  |  | in progress | Boss_Ashley_Skill_Execution_State5 | Mon_Boss_Body_B01_Execu_State5
|  |  | state7第一段 |  |  | in progress | Boss_Ashley_Skill_Execution_State7 | Mon_Boss_Body_B01_Execu_State7
|  |  | state7第二段 |  |  | in progress |  | Mon_Boss_Body_B01_Execu_State7_2nd
|  |  | state8第一段 |  |  | in progress | Boss_Ashley_Skill_Execution_State8 | Mon_Boss_Body_B01_Execu_State8
|  |  | state8第二段 |  |  | in progress |  | Mon_Boss_Body_B01_Execu_State8_2nd
|  |  | state8第三段 |  |  | in progress |  | Mon_Boss_Body_B01_Execu_State8_3rd
|  |  | state9第一段 |  |  | in progress | Boss_Ashley_Skill_Execution_State9 | Mon_Boss_Body_B01_Execu_State9
|  |  | state9第二段 |  |  | in progress | Boss_Ashley_Skill_Execution_State9 | Mon_Boss_Body_B01_Execu_State9_2nd

## Mobs
需求模块 Require Module | 二级模块 Second Module | 需求名 Require Name | 装甲类型 Material | 类别 Category | 需求技能描述 Skill Description | 级别 Monster Level | 动画编辑器配置文件名 | *音频配置位置（动画animation） | 音频资源交付时间 Due Time | 音频状态 Status | 音效描述 Sound event Description | 原音效名Old | 原音效名 | 音效名 Sample Name | 样本数量 Sample Number | 技能播放方式 One shot/Loop | 声音绑定方式 Sound Binding Method | 备注 Remarks | 反馈 feedback
[11 empty] | 例如：武器声音体现比较沉重，带有金属质感。动作旋转声需带有强烈风声，最后一下击中感声音体现能量最强 |  |  | Mon_MobXX_行为_技能_状态 |  | 循环播放; 单次播放; 弹道飞行 | 特效编辑器 动作编辑器 技能编辑器
狼人Werewolf 最常见怪物，路人揭发身份后变身狼人，包含7种反应属性并在外观上分色 铁血生物狼人，经过液态金属注射改造而成 中大型近战单位，攻击欲望强烈，爪击撕咬为主 |  |  | 音效设计方向： 尖锐、兽性威胁，音效表现主要通过偏人形发声的兽人呼喝声突出威胁性。 正式资源使用refomer等插件对怪物叫声进行重采样和设计更贴合实际动画表现。 整体音效动态要大，触发attack短
M01狼人 | 技能1 | 起手 | 生物 |  | 左右轮流挥舞利爪造成两次打击，伴随两次位移 | 精英 |  |  |  | in progress | 音效重点在第二次爪击，使用金属元素体现尖锐爪击 | Mon_Werewolf_Atk1 | Mon_Mob_Skill_M01_Atk1 | Mon_Mob_Skill_M01_Atk1 | 1
|  | 2段 | [7 empty] | in progress |  |  |  | Mon_Mob_Skill_M01_Atk1_2nd | 1
|  | 3段 | [7 empty] | in progress |  |  |  | Mon_Mob_Skill_M01_Atk1_3rd | 1
|  | 4段 | [7 empty] | in progress |  |  |  | Mon_Mob_Skill_M01_Atk1_4th | 1
|  | 5段 | [7 empty] | in progress |  |  |  | Mon_Mob_Skill_M01_Atk1_5th | 1
|  | 6段 | [7 empty] | in progress |  |  |  | Mon_Mob_Skill_M01_Atk1_6th | 1
| 技能2 | 起手 |  |  | 跳起在空中然后用爪下劈，造成一次打击 |  |  |  |  | in progress | 音效重点在第二次下劈 | Mon_Werewolf_Skill2 | Mon_Mob_Skill_M01_Atk2 | Mon_Mob_Skill_M01_Atk2 | 1
|  | 2段 | [7 empty] | in progress |  |  |  | Mon_Mob_Skill_M01_Atk2_2nd | 1
|  | 3段 | [7 empty] | in progress |  |  |  | Mon_Mob_Skill_M01_Atk2_3rd | 1
|  | 4段 | [7 empty] | in progress |  |  |  | Mon_Mob_Skill_M01_Atk2_4th | 1
| 技能3 | 起手 | [7 empty] | in progress |  |  |  | Mon_Mob_Skill_M01_Atk3 | 1
|  | 2段 | [7 empty] | in progress |  |  |  | Mon_Mob_Skill_M01_Atk3_2nd | 1
|  | 3段 | [7 empty] | in progress |  |  |  | Mon_Mob_Skill_M01_Atk3_3rd | 1
|  | 4段 | [7 empty] | in progress |  |  |  | Mon_Mob_Skill_M01_Atk3_4th | 1
|  | 5段 | [7 empty] | in progress |  |  |  | Mon_Mob_Skill_M01_Atk3_5th | 1
|  | 收招 | [7 empty] | in progress |  |  |  | Mon_Mob_Skill_M01_Atk3_End | 1
| 技能4 | [8 empty] | in progress |  |  |  | Mon_Mob_Skill_M01_Atk4 | 1
| 技能5 | 起手 | [7 empty] | in progress |  |  |  | Mon_Mob_Skill_M01_Atk5 | 1
|  | 2段 | [7 empty] | in progress |  |  |  | Mon_Mob_Skill_M01_Atk5_2nd | 1
|  | 3段 | [7 empty] | in progress |  |  |  | Mon_Mob_Skill_M01_Atk5_3rd | 1
|  | 4段 | [7 empty] | in progress |  |  |  | Mon_Mob_Skill_M01_Atk5_4th | 1
|  | 5段 | [7 empty] | in progress |  |  |  | Mon_Mob_Skill_M01_Atk5_5th | 1
|  | 6段 | [7 empty] | in progress |  |  |  | Mon_Mob_Skill_M01_Atk5_6th | 1
|  | 7段 | [7 empty] | in progress |  |  |  | Mon_Mob_Skill_M01_Atk5_7th | 1
|  | 8段 | [7 empty] | in progress |  |  |  | Mon_Mob_Skill_M01_Atk5_8th | 1
|  | 收招 | [7 empty] | in progress |  |  |  | Mon_Mob_Skill_M01_Atk5_End | 1
| 技能10 | [8 empty] | in progress |  |  |  | Mon_Mob_Skill_M01_Atk10 | 1
| 技能11 | 起手 | [7 empty] | in progress |  |  |  | Mon_Mob_Skill_M01_Atk11 | 1
|  | 2段 | [7 empty] | in progress |  |  |  | Mon_Mob_Skill_M01_Atk11_2nd | 1
|  | 3段 | [7 empty] | in progress |  |  |  | Mon_Mob_Skill_M01_Atk11_3rd | 1
|  | 4段 | [7 empty] | in progress |  |  |  | Mon_Mob_Skill_M01_Atk11_4th | 1
|  | 5段 | [7 empty] | in progress |  |  |  | Mon_Mob_Skill_M01_Atk11_5th | 1
|  | 6段 | [7 empty] | in progress |  |  |  | Mon_Mob_Skill_M01_Atk11_6th | 1
|  | 7段 | [7 empty] | in progress |  |  |  | Mon_Mob_Skill_M01_Atk11_7th | 1
|  | 收招 | [7 empty] | in progress |  |  |  | Mon_Mob_Skill_M01_Atk11_End | 1
| 垫步 |  |  |  | 一步内的闪避动作 |  |  |  |  | in progress |  | Mon_Werewolf_Step | Mon_Mob_Skill_M01_Step | Mon_Mob_Skill_M01_Step | 3
| 死亡 | 原地死亡 |  |  | 原地瘫倒（毒死） |  |  |  |  | in progress |  | Mon_Werewolf_Die | Mon_Mob_Skill_M01_Death | Mon_Mob_Skill_M01_Death | 1
| 起身 | [8 empty] | in progress |  | Mon_Werewolf_GetUp | Mon_Mob_Foley_M01_Getup | Mon_Mob_Foley_M01_Getup | 1
| 通用Foley | 跑 | [7 empty] | in progress | 大部分是四脚着地跑的情况 | Mon_Werewolf_Gen_Walk | Mon_Mob_Foley_M01_Walk | Mon_Mob_Foley_M01_Run | 3
| shout voice | 变身入战 | [7 empty] | in progress |  | Mon_Werewolf_Shout_Born_Transform | Mon_Mob_Shout_M01_Born_Trans | Mon_Mob_Shout_M01_Born_Trans | 3
|  | 威胁grunt | [7 empty] | in progress |  | Mon_Werewolf_Shout_Threaten | Mon_Mob_Shout_M01_Threaten | Mon_Mob_Shout_M01_Threaten | 3
|  | 重受击 | [7 empty] | in progress |  | Mon_Werewolf_Shout_HeavyHit | Mon_Mob_Shout_M01_Hit_Hvy | Mon_Mob_Shout_M01_Hit_Hvy | 3
|  | 轻死亡 | [7 empty] | in progress |  | Mon_Werewolf_Shout_Die | Mon_Mob_Shout_M01_Death | Mon_Mob_Shout_M01_Death | 3
|  | 倒地后起身 | [7 empty] | in progress |  | Mon_Werewolf_Shout_GetUp | Mon_Mob_Shout_M01_Getup | Mon_Mob_Shout_M01_Getup | 3
|  | 冲刺 | [7 empty] | in progress |  | Mon_Werewolf_Shout_Sprint | Mon_Mob_Shout_M01_Sprint | Mon_Mob_Shout_M01_Sprint | 3
|  | 喘气/低鸣 | [7 empty] | in progress |  |  |  | Mon_Mob_Shout_M01_Breath | 4
|  | 轻攻击 | [7 empty] | in progress |  | Mon_Werewolf_Shout_Atk | Mon_Mob_Shout_M01_Atk | Mon_Mob_Shout_M01_Atk | 3
|  | 重攻击 | [7 empty] | in progress |  | Mon_Werewolf_Shout_HeavyAtk | Mon_Mob_Shout_M01_Atk_Hvy | Mon_Mob_Shout_M01_Atk_Hvy | 3
|  | 下攻击 | [7 empty] | in progress |  | Mon_Werewolf_Shout_SmashDown | Mon_Mob_Shout_M01_Atk_D | Mon_Mob_Shout_M01_Atk_D | 3
|  | 位移（垫步） | [7 empty] | in progress |  | Mon_Werewolf_Shout_Step | Mon_Mob_Shout_M01_Step | Mon_Mob_Shout_M01_Step | 3
僵尸蜡烛人Candleman 势力：净化者 被改造成业态金属身体的可怜人，身体呈现蜡一样的质地，很容易点燃，必须补充新的液态金属才能维持生命，否则会逐渐萎缩彻底消失。蜡烛人隐藏在路人里，与玩家交战时身体突然燃烧，衣服烧尽，展现蜡烛人本体。 主要（血液）属性：点燃 战斗定位：液态金属僵尸，产生的资源多余制造的威胁，常见怪物。 |  |  | 音效设计方向：听感偏僵尸，没有粘稠和血液的部分突出燃烧和可燃性，整体偏物理和写实的音效元素 音效关键词：异类、黑暗、诡异、消极
M02僵尸蜡烛人 | 入战表现 |  | 生物 |  | 跪趴站起来，从特效液体中出生站起来 | 小怪 |  |  |  | in progress | 脑补白银液体暂时没有特效，此版本稍微做些粘稠声音即可 | Mon_Candleman_Born | Mon_Mob_Skill_M02_Born | Mon_Mob_Skill_M02_Born | 1
| 技能1 |  |  |  | 单位有肢体破坏系统，缺失右手也会用另一只手攻击 |  |  |  |  | in progress | 尽量左右手挥舞通用 | Mon_Candleman_Atk1 | Mon_Mob_Skill_M02_Atk1 | Mon_Mob_Skill_M02_Atk1 | 2
| 技能2 |  |  |  | 同上 |  |  |  |  | in progress |  | Mon_Candleman_Atk2 | Mon_Mob_Skill_M02_Atk2 | Mon_Mob_Skill_M02_Atk2 | 2
| 技能3 |  |  |  | 只会在缺失双手时使用，腰部发力 |  |  |  |  | in progress | 连招技能需要连起来听，注意同材质和音效节奏 | Mon_Candleman_Atk3 | Mon_Mob_Skill_M02_Atk3 | Mon_Mob_Skill_M02_Atk3 | 1
| 技能4 | 蓄力 | [7 empty] | in progress | 炮弹声对比女仆散弹，不可以比主角色华丽和威力 |  |  | Mon_Mob_Skill_M02_Atk4_Pre | 2
|  | 发射 |  |  | 手臂变成枪口，发射炮弹 |  |  |  |  | in progress |  | Mon_Candleman_Atk4 | Mon_Mob_Skill_M02_Atk4 | Mon_Mob_Skill_M02_Atk4 | 2
| 自爆技能 | [8 empty] | in progress |  |  |  | Mon_Mob_Skill_M02_Death_Skill | 1
| Die | 死亡倒地 | [7 empty] | in progress | 重重倒地，夸张表达，给玩家成就感，但并非一层低频，需要多叠几层元素 | Mon_Candleman_Gen_Die | Mon_Mob_Skill_M02_Death | Mon_Mob_Skill_M02_Death | 3
| action | 跑 | [7 empty] | in progress | 注意怪物蜡烛人材质，重量不会过大，甚至是比较轻的存在 | Mon_Candleman_Gen_Run | Mon_Mob_Foley_M02_Run | Mon_Mob_Foley_M02_Run | 4
|  | 死亡倒地 | [7 empty] | in progress | 重重倒地，夸张表达，给玩家成就感，但并非一层低频，需要多叠几层元素 | Mon_Candleman_Gen_Die | Mon_Mob_Foley_M02_Death | Mon_Mob_Foley_M02_Death | 3
|  | 起身 | [7 empty] | in progress |  | Mon_Candleman_Gen_GetUp | Mon_Mob_Foley_M02_Getup | Mon_Mob_Foley_M02_Getup | 3
|  | 通用倒地非死亡 | [7 empty] | in progress | 落地后弹起再重重落地，倒地fall的元素叠加 | Mon_Candleman_Gen_FallDown | Mon_Mob_Foley_M02_Fall_Down | Mon_Mob_Foley_M02_Fall_Down | 1
| shout | 轻攻击 | [7 empty] | in progress | https://www.youtube.com/watch?v=-405-agP2FU | Mon_Candleman_Shout_Atk | Mon_Mob_Shout_M02_Atk | Mon_Mob_Shout_M02_Atk | 3
|  | 重攻击 | [7 empty] | in progress |  | Mon_Candleman_Shout_HeavyAtk | Mon_Mob_Shout_M02_Atk_Hvy | Mon_Mob_Shout_M02_Atk_Hvy | 3
|  | 重受击 | [7 empty] | in progress |  | Mon_Candleman_Shout_HeavyHit | Mon_Mob_Shout_M02_Hit_Hvy | Mon_Mob_Shout_M02_Hit_Hvy | 3
|  | 轻死亡 | [7 empty] | in progress | 普通受击后接的死亡用 | Mon_Candleman_Shout_Die | Mon_Mob_Shout_M02_Death | Mon_Mob_Shout_M02_Death | 4
|  | Idle | [7 empty] | in progress |  |  |  | Mon_Mob_Shout_M02_Idle | 4
|  | Struggle，用于SK11 | [7 empty] | in progress |  | Mon_Candleman_Shout_Struggle | Mon_Mob_Shout_M02_Struggle | Mon_Mob_Shout_M02_Struggle | 5
铁甲面 Enforcer |  |  | 音效设计方向：
M03铁甲面 | 技能1（冲锋枪） | [8 empty] | in progress |  |  |  | Mon_Mob_Skill_M03_Smg_Atk1 | 1
| 技能2（冲锋枪） | 起手 | [7 empty] | in progress |  |  |  | Mon_Mob_Skill_M03_Smg_Atk2 | 1
|  | 射击 | [7 empty] | in progress |  |  |  | Mon_Mob_Skill_M03_Smg_Atk2_Shoot | 1
| 技能1（电棍） | [8 empty] | in progress |  |  |  | Mon_Mob_Skill_M03_Eb_Atk1 | 1
| 技能2（电棍） | [8 empty] | in progress |  |  |  | Mon_Mob_Skill_M03_Eb_Atk2 | 1
| 技能2（电棍）爆破 | [8 empty] | in progress |  |  |  | Mon_Mob_Skill_M03_Eb_Atk2_2nd | 1
| 技能3（电棍） | [8 empty] | in progress |  |  |  | Mon_Mob_Skill_M03_Eb_Atk3 | 1
| 技能4（电棍） | [8 empty] | in progress |  |  |  | Mon_Mob_Skill_M03_Eb_Atk4 | 1
| 技能5（电棍） | [8 empty] | in progress |  |  |  | Mon_Mob_Skill_M03_Eb_Atk5 | 1
| action | 死亡倒地 | [7 empty] | in progress |  |  |  | Mon_Mob_Skill_M03_Death | 1
|  | 跑 | [7 empty] | in progress |  |  |  | Mon_Mob_Foley_M03_Run | 4
无头骑士 EmptyArmor |  |  | 音效设计方向： 《黑暗之魂》中的古达（体型大小最贴近） 《艾尔达发环》中的熔炉骑士 《战神》中的荒野浪人
M04无头骑士 | 技能1 | 起手 | 金属 |  | 奔跑接近玩家，挥舞巨斧向前方挥砍一次，再砸地劈砍一次 | 精英 |  |  |  | in progress |  |  |  | Mon_Mob_Skill_M04_Atk1 | 1
|  | 巨斧挥起 | [7 empty] | in progress |  |  |  | Mon_Mob_Skill_M04_Atk1_2nd | 1
|  | 巨斧砸地 | [7 empty] | in progress |  |  |  | Mon_Mob_Skill_M04_Atk1_3rd | 1
|  | 收招 | [7 empty] | in progress |  |  |  | Mon_Mob_Skill_M04_Atk1_End | 1
| 技能2 | 起手 |  |  | 转身抡斧一周 |  |  |  |  | in progress |  |  |  | Mon_Mob_Skill_M04_Atk2 | 1
|  | 巨斧挥砍 | [7 empty] | in progress |  |  |  | Mon_Mob_Skill_M04_Atk2_2nd | 1
|  | 收招 | [7 empty] | in progress |  |  |  | Mon_Mob_Skill_M04_Atk2_End | 1
| 技能3 | 起手 |  |  | 跳砸 |  |  |  |  | in progress |  |  |  | Mon_Mob_Skill_M04_Atk3 | 1
|  | 跳起 | [7 empty] | in progress |  |  |  | Mon_Mob_Skill_M04_Atk3_2nd | 1
|  | 砸地 | [7 empty] | in progress |  |  |  | Mon_Mob_Skill_M04_Atk3_3rd | 1
|  | 收招 |  |  | 收起巨斧回到原位 |  |  |  |  | in progress |  |  |  | Mon_Mob_Skill_M04_Atk3_End | 1
| 技能4 | 后撤 |  |  | 闪避 |  |  |  |  | in progress |  |  |  | Mon_Mob_Skill_M04_Atk4 | 1
| 技能5 | 起手 |  |  | 五连击 |  |  |  |  | in progress |  |  |  | Mon_Mob_Skill_M04_Atk5 | 1
|  | 单脚踏地 | [7 empty] | in progress |  |  |  | Mon_Mob_Skill_M04_Atk5_2nd | 1
|  | 1段攻击 | [7 empty] | in progress |  |  |  | Mon_Mob_Skill_M04_Atk5_3rd | 1
|  | 2段攻击 | [7 empty] | in progress |  |  |  | Mon_Mob_Skill_M04_Atk5_4th | 1
|  | 3段砸地 | [7 empty] | in progress |  |  |  | Mon_Mob_Skill_M04_Atk5_5th | 1
|  | 3段攻击 | [7 empty] | in progress |  |  |  | Mon_Mob_Skill_M04_Atk5_6th | 1
|  | 4段攻击 | [7 empty] | in progress |  |  |  | Mon_Mob_Skill_M04_Atk5_7th | 1
|  | 5段举斧 | [7 empty] | in progress |  |  |  | Mon_Mob_Skill_M04_Atk5_8th | 1
|  | 5段砸地 | [7 empty] | in progress |  |  |  | Mon_Mob_Skill_M04_Atk5_9th | 1
| 技能6 | 起手 |  |  | 二连挥砍，势大力沉 |  |  |  |  | in progress |  |  |  | Mon_Mob_Skill_M04_Atk6 | 1
|  | 挥砍1段 | [7 empty] | in progress |  |  |  | Mon_Mob_Skill_M04_Atk6_2nd | 1
|  | 挥砍2段 | [7 empty] | in progress |  |  |  | Mon_Mob_Skill_M04_Atk6_3rd | 1
|  | 收招 | [7 empty] | in progress |  |  |  | Mon_Mob_Skill_M04_Atk6_End | 1
| 技能7 | 出招 |  |  | 大风车5连挥砍 |  |  |  |  | in progress |  |  |  | Mon_Mob_Skill_M04_Atk7 | 1
|  | 挥砍1段 | [7 empty] | in progress |  |  |  | Mon_Mob_Skill_M04_Atk7_2nd | 1
|  | 挥砍2段 | [7 empty] | in progress |  |  |  | Mon_Mob_Skill_M04_Atk7_3rd | 1
|  | 挥砍3段 | [7 empty] | in progress |  |  |  | Mon_Mob_Skill_M04_Atk7_4th | 1
|  | 挥砍4段 | [7 empty] | in progress |  |  |  | Mon_Mob_Skill_M04_Atk7_5th | 1
|  | 挥砍5段 | [7 empty] | in progress |  |  |  | Mon_Mob_Skill_M04_Atk7_6th | 1
|  | 收招 | [7 empty] | in progress |  |  |  | Mon_Mob_Skill_M04_Atk7_End | 1
| action | 移动 |  |  | 盔甲材质的脚步声（现阶段暂时缺少挂接机制） |  |  |  |  | in progress |  |  |  | Mon_Mob_Foley_M04_Run | 4
|  | 原地死亡倒地 |  |  | 身体（盔甲）逐步散架，最终倒地（GE挂接） |  |  |  |  | in progress |  |  |  | Mon_Mob_Foley_M04_Death | 1

## Imp&Weapon（命中）
武器 Require Module | 攻击方式 Second Module | 力度 Require Name | 状态 Status | 音效名 Sample Name | 音频资源交付时间 Due Time | 备注 Remarks
剑 | 斩击 | 轻 | in progress | Imp_Sword_Chop_Flesh_Lit
|  | 中 | in progress | Imp_Sword_Chop_Flesh_Mid
|  | 重 | in progress | Imp_Sword_Chop_Flesh_Hvy
|  | 特殊暴击 | in progress | Imp_Sword_Chop_Flesh_Cri
|  | 中-金属 | in progress | Imp_Sword_Chop_Metal_Mid
| 穿刺 | 中 | in progress | Imp_Sword_Stab_Flesh_Mid
大剑 | 斩击 | 轻 | in progress | Imp_Greatsword_Chop_Flesh_Lit
| 斩击 | 中 | in progress | Imp_Greatsword_Chop_Flesh_Mid
| 斩击 | 重 | in progress | Imp_Greatsword_Chop_Flesh_Hvy
刀 | 斩击 | 中 | in progress | Imp_Knife_Chop_Flesh_Mid
| 斩击 | 重 | in progress | Imp_Knife_Chop_Flesh_Hvy
| 斩击 | 特殊暴击 | in progress | Imp_Knife_Chop_Flesh_Cri
爪子 | 抓击 | 中 | in progress | Imp_Claw_Scratch_Flesh_Mid
| 抓击 | 重 | in progress | Imp_Claw_Scratch_Flesh_Hvy
拳套 | 拳击 | 中 | in progress | Imp_Fist_Punch_Flesh_Mid
踢腿 | 扫腿 | 中 | in progress | Imp_Kick_Punch_Flesh_Mid
手枪 | 射击 | 轻 | in progress | Imp_Handgun_Shot_Flesh_Lit
| 射击 | 中 | in progress | Imp_Handgun_Shot_Flesh_Mid
机关枪 | 射击 | 中 | in progress | Imp_Mcgun_Shot_Flesh_Mid
| 射击 | 特殊暴击 | in progress | Imp_Mcgun_Shot_Flesh_Cri
利齿 | 撕咬 | 中 | in progress | Imp_Teeth_Bite_Flesh_Mid
盾牌 | 冲撞 | 特殊暴击 | in progress | Imp_Shield_Punch_Flesh_Cri
毒液 | 喷射 | 中 | in progress | Imp_Poison_Hit_Flesh_Mid
火焰 | 发射 | 中 | in progress | Imp_Fire_Hit_Flesh_Mid
护盾 | 通用 | 中 | in progress | Imp_Barrier_Hit_Gen_Mid
护盾 | 通用 | 重 | in progress | Imp_Barrier_Hit_Gen_Hvy

## Hero（通用移动）
需求模块 Require Module | 移动动作 Second Module | 材质名 Require Name | 设计要点 | 动作描述说明 Description | 限定武器 | 状态 Status | *编辑器配置文件名（包括路径） | 音频资源交付时间 Due Time | 旧音效命名 | 音效名 Sample Name | 参考视频名称 Reference Video Name | 音效描述 Sound event Description | 样本数量 Numbers | 备注 Remarks | 优化 | 样本问题及优化方向 V1 | 补充 V1 | 样本问题及优化方向 V2 | 补充 V2 | 样本问题及优化方向 V3 | 补充 V3 | 样本问题及优化方向 V4 | 补充 V4 | 样本问题及优化方向 V5 | 补充 V5
|  |  | 不区分非战和战斗状态，以非战形态脚步为主 | [5 empty] | 角色名_FS_鞋型_材质_脚步类型 | Char_Mov_Gen_通用鞋型_移动类型_材质 |  | 前后必须剪干净，响度必须控制 | random命名01 02 03…… |  | 迭代进度 | 声音设计师填写 | 策划填写
女高跟通用
| 走 | Dirt | ard-21LUFS 女士粗跟鞋，跟的声音不易过大而显得过女性化，尽量通用感强 普通衣物，带皮饰，金属点缀 | 配速300cm/s |  | done |  |  | Player_FS_HighHeel_Dirt_Walk_01 | Char_Mov_Gen_HHeel_Walk_Dirt |  | 泥地，通用材质 | 6
|  | Rock |  |  |  | done |  |  | Player_FS_HighHeel_Rock_Walk | Char_Mov_Gen_HHeel_Walk_Rock |  | 石板，大理石，有一定质量的石头，较为光滑 | 6
|  | Sand |  |  |  | to do
|  | Grass |  |  |  | to do
|  | Wood |  |  |  | to do |  |  | Player_FS_HighHeel_Wood_Walk | Char_Mov_Gen_HHeel_Walk_Wood |  | 木质地板
|  | Water |  |  |  | to do
|  | Metal |  |  |  | to do
| 跑 | Dirt |  | 配速500cm/s，最常使用 |  | done |  |  | Player_FS_HighHeel_Dirt_Run | Char_Mov_Gen_HHeel_Run_Dirt |  |  | 6
| 疾跑冲刺 | Dirt |  | 配速650cm/s，shift冲刺 |  | done |  |  | Player_FS_HighHeel_Dirt_Sprint | Char_Mov_Gen_HHeel_Sprint_Dirt |  |  | 6
| 停 |  |  | 被打断停止 |  | done |  |  | Player_FS_HighHeel_Dirt_End | Char_Mov_Gen_HHeel_End_Dirt |  | 走跑通用，单个 | 6
| 转向 |  |  |  |  | to do | [5 empty] | 先不做 | /
| Dodge一大步 |  |  | 转圈 进编辑器看 |  | to do | [6 empty] | /
| step一小步 | 滑行 |  |  |  | to do |  |  | Player_FS_HighHeel_Gen_Slide | Char_Mov_Gen_HHeel_Slide_Gen |  | 脚步擦地面声，loop | 3
|  | 左右偏向 |  | 滑行过程中，可水平移动角色 |  | to do |  |  | Player_FS_HighHeel_Gen_Slide_Dev | Char_Mov_Gen_HHeel_Slide_Gen_Dev |  | 偏向一般为音调升高，loop | 3
|  | 停 |  |  |  | to do |  |  | Player_FS_HighHeel_Gen_Slide_Stop | Char_Mov_Gen_HHeel_Slide_Gen_Stop |  |  | 3
| 蹲走 |  |  | 移动模式下按下蹲进行蹲行状态，步行移动速度 |  | done |  |  | Player_FS_HighHeel_Dirt_Squat | Char_Mov_Gen_HHeel_Squat_Dirt |  |  | 5
| 攀爬 |  |  |  |  | done |  |  | Player_FS_HighHeel_Gen_Climb | Char_Mov_Gen_HHeel_Climb_Gen |  | 偏向摩擦，跟的声音几乎没有 | 5
| 跳 |  | 主要衣物声音，脚步动作一点 | 起跳动作 |  | done |  |  | Player_FS_HighHeel_Dirt_Jump | Char_Mov_Gen_HHeel_Jump_Dirt |  |  | 3
| 落地大 |  |  | 双脚落地 |  | done |  |  | Player_FS_HighHeel_Dirt_FallHeavy | Char_Mov_Gen_HHeel_Fall_Dirt_Hvy |  | 两脚几乎同时下 | 3
| 落地小 |  |  |  |  | done |  |  | Player_FS_HighHeel_Dirt_FallLand | Char_Mov_Gen_HHeel_Fall_Dirt_Lit |  | 听感通用，两脚稍错开下 | 3
筒靴（带跟）
| 走 | Dirt | ard-21LUFS 男女通用，带根筒靴，不强调高跟 轻甲，皮靴上有零碎装饰物件 | 配速300cm/s |  | done |  |  | Player_FS_HeelBoots_Dirt_Walk_01 | Char_Mov_Gen_Boot_Walk_Dirt |  | 泥地，通用材质 | 6
|  | Rock |  |  |  | done |  |  | Player_FS_HeelBoots_Rock_Walk | Char_Mov_Gen_Boot_Walk_Rock |  | 石板，大理石，有一定质量的石头，较为光滑 | 6
|  | Sand |  |  |  | to do
|  | Grass |  |  |  | to do
|  | Wood |  |  |  | to do |  |  | Player_FS_HeelBoots_Wood_Walk | Char_Mov_Gen_Boot_Walk_Wood
|  | Water |  |  |  | to do
|  | Metal |  |  |  | to do
| 跑 | Dirt |  | 配速500cm/s，最常使用 |  | done |  |  | Player_FS_HeelBoots_Dirt_Run | Char_Mov_Gen_Boot_Run_Dirt |  |  | 6
| 疾跑冲刺 | Dirt |  | 配速650cm/s，shift冲刺 |  | done |  |  | Player_FS_HeelBoots_Dirt_Sprint | Char_Mov_Gen_Boot_Sprint_Dirt |  |  | 6
| 停 |  |  | 被打断停止 |  | done |  |  | Player_FS_HeelBoots_Dirt_End | Char_Mov_Gen_Boot_End_Dirt |  | 走跑通用，单个 | 6
| 转向 |  |  |  |  | to do | [5 empty] | 先不做 | /
| Dodge一大步 |  |  | 转圈 进编辑器看 |  | to do | [6 empty] | /
| step一小步 | 滑行 |  |  |  | to do |  |  | Player_FS_HeelBoots_Gen_Slide | Char_Mov_Gen_Boot_Slide_Gen |  | 脚步擦地面声，loop | 3
|  | 左右偏向 |  | 滑行过程中，可水平移动角色 |  | to do |  |  | Player_FS_HeelBoots_Gen_Slide_Dev | Char_Mov_Gen_Boot_Slide_Gen_Dev |  | 偏向一般为音调升高，loop | 3
|  | 停 |  |  |  | to do |  |  | Player_FS_HeelBoots_Gen_Slide_Stop | Char_Mov_Gen_Boot_Slide_Gen_Stop |  |  | 3
| 蹲走 |  |  | 移动模式下按下蹲进行蹲行状态，步行移动速度 |  | done |  |  | Player_FS_HeelBoots_Dirt_Squat | Char_Mov_Gen_Boot_Squat_Dirt |  |  | 5
| 攀爬 |  |  |  |  | done |  |  | Player_FS_HeelBoots_Gen_Climb | Char_Mov_Gen_Boot_Climb_Gen |  | 偏向摩擦，跟的声音几乎没有 | 5
| 跳 |  | 主要衣物声音，脚步动作一点 | 起跳动作 |  | done |  |  | Player_FS_HeelBoots_Dirt_Jump | Char_Mov_Gen_Boot_Jump_Dirt |  |  | 3
| 落地大 |  |  | 双脚落地 |  | done |  |  | Player_FS_HeelBoots_Dirt_FallHeavy | Char_Mov_Gen_Boot_Fall_Dirt_Hvy |  | 两脚几乎同时下 | 3
| 落地小 |  |  |  |  | done |  |  | Player_FS_HeelBoots_Dirt_FallLand | Char_Mov_Gen_Boot_Fall_Dirt_Lit |  | 听感通用，两脚稍错开下 | 3
平底皮鞋
| 走 | Dirt | ard-21LUFS 女 普通衣物，带装饰，偏女性化装饰，参考富婆萝莉 | 配速300cm/s |  | done |  |  | Player_FS_HighHeel_Dirt_Walk_01 | Char_Mov_Gen_MJ_Walk_Dirt |  | 泥地，通用材质 | 6
|  | Rock |  |  |  | done |  |  | Player_FS_HighHeel_Rock_Walk | Char_Mov_Gen_MJ_Walk_Rock |  | 石板，大理石，有一定质量的石头，较为光滑 | 6
|  | Sand |  |  |  | to do
|  | Grass |  |  |  | to do
|  | Wood |  |  |  | to do
|  | Water |  |  |  | to do
|  | Metal |  |  |  | to do
| 跑 | Dirt |  | 配速500cm/s，最常使用 |  | done |  |  | Player_FS_HighHeel_Dirt_Run | Char_Mov_Gen_MJ_Run_Dirt |  |  | 6
| 疾跑冲刺 | Dirt |  | 配速650cm/s，shift冲刺 |  | done |  |  | Player_FS_HighHeel_Dirt_Sprint | Char_Mov_Gen_MJ_Sprint_Dirt |  |  | 6
| 停 |  |  | 被打断停止 |  | done |  |  | Player_FS_HighHeel_Dirt_End | Char_Mov_Gen_MJ_End_Dirt |  | 走跑通用，单个 | 6
| 转向 |  |  |  |  | to do | [5 empty] | 先不做 | /
| Dodge一大步 |  |  | 转圈 进编辑器看 |  | to do | [6 empty] | /
| step一小步 | 滑行 |  |  |  | to do |  |  | Player_FS_HighHeel_Gen_Slide | Char_Mov_Gen_MJ_Slide_Gen |  | 脚步擦地面声，loop | 3
|  | 左右偏向 |  | 滑行过程中，可水平移动角色 |  | to do |  |  | Player_FS_HighHeel_Gen_Slide_Dev | Char_Mov_Gen_MJ_Slide_Gen_Dev |  | 偏向一般为音调升高，loop | 3
|  | 停 |  |  |  | to do |  |  | Player_FS_HighHeel_Gen_Slide_Stop | Char_Mov_Gen_MJ_Slide_Gen_Stop |  |  | 3
| 蹲走 |  |  | 移动模式下按下蹲进行蹲行状态，步行移动速度 |  | done |  |  | Player_FS_HighHeel_Dirt_Squat | Char_Mov_Gen_MJ_Squat_Dirt |  |  | 5
| 攀爬 |  |  |  |  | done |  |  | Player_FS_HighHeel_Gen_Climb | Char_Mov_Gen_MJ_Climb_Gen |  | 偏向摩擦，跟的声音几乎没有 | 5
| 跳 |  | 主要衣物声音，脚步动作一点 | 起跳动作 |  | done |  |  | Player_FS_HighHeel_Dirt_Jump | Char_Mov_Gen_MJ_Jump_Dirt |  |  | 3
| 落地大 |  |  | 双脚落地 |  | done |  |  | Player_FS_HighHeel_Dirt_FallHeavy | Char_Mov_Gen_MJ_Fall_Dirt_Hvy |  | 两脚几乎同时下 | 3
| 落地小 |  |  |  |  | done |  |  | Player_FS_HighHeel_Dirt_FallLand | Char_Mov_Gen_MJ_Fall_Dirt_Lit |  | 听感通用，两脚稍错开下 | 3
细高跟鞋 | 走 | Dirt | ard-21LUFS 女式尖头细高跟鞋 带装饰，偏女性化装饰，参考女主 | 配速300cm/s |  | done |  |  | Player_FS_StilettoHeel_Dirt_Walk_01 | Char_Mov_Gen_SHeel_Walk_Dirt |  | 泥地，通用材质 | 6
|  | Rock |  |  |  | done |  |  | Player_FS_StilettoHeel_Rock_Walk | Char_Mov_Gen_SHeel_Walk_Rock |  | 石板，大理石，有一定质量的石头，较为光滑 | 6
|  | Sand |  |  |  | to do
|  | Grass |  |  |  | to do
|  | Wood |  |  |  | to do |  |  | Player_FS_StilettoHeel_Wood_Walk | Char_Mov_Gen_SHeel_Walk_Wood
|  | Water |  |  |  | to do
|  | Metal |  |  |  | to do
| 跑 | Dirt |  | 配速500cm/s，最常使用 |  | done |  |  | Player_FS_StilettoHeel_Dirt_Run | Char_Mov_Gen_SHeel_Run_Dirt |  |  | 6
| 疾跑冲刺 | Dirt |  | 配速650cm/s，shift冲刺 |  | done |  |  | Player_FS_StilettoHeel_Dirt_Sprint | Char_Mov_Gen_SHeel_Sprint_Dirt |  |  | 6
| 停 |  |  | 被打断停止 |  | done |  |  | Player_FS_StilettoHeel_Dirt_End | Char_Mov_Gen_SHeel_End_Dirt |  | 走跑通用，单个 | 6
| 转向 |  |  |  |  | to do | [5 empty] | 先不做 | /
| Dodge一大步 |  |  | 转圈 进编辑器看 |  | to do | [6 empty] | /
| step一小步 | 滑行 |  |  |  | to do |  |  | Player_FS_StilettoHeel_Gen_Slide | Char_Mov_Gen_SHeel_Slide_Gen |  | 脚步擦地面声，loop | 3
|  | 左右偏向 |  | 滑行过程中，可水平移动角色 |  | to do |  |  | Player_FS_StilettoHeel_Gen_Slide_Dev | Char_Mov_Gen_SHeel_Slide_Gen_Dev |  | 偏向一般为音调升高，loop | 3
|  | 停 |  |  |  | to do |  |  | Player_FS_StilettoHeel_Gen_Slide_Stop | Char_Mov_Gen_SHeel_Slide_Gen_Stop |  |  | 3
| 蹲走 |  |  | 移动模式下按下蹲进行蹲行状态，步行移动速度 |  | done |  |  | Player_FS_StilettoHeel_Dirt_Squat | Char_Mov_Gen_SHeel_Squat_Dirt |  |  | 5
| 攀爬 |  |  |  |  | done |  |  | Player_FS_StilettoHeel_Gen_Climb | Char_Mov_Gen_SHeel_Climb_Gen |  | 偏向摩擦，跟的声音几乎没有 | 5
| 跳 |  | 主要衣物声音，脚步动作一点 | 起跳动作 |  | done |  |  | Player_FS_StilettoHeel_Dirt_Jump | Char_Mov_Gen_SHeel_Jump_Dirt |  |  | 3
| 落地大 |  |  | 双脚落地 |  | done |  |  | Player_FS_StilettoHeel_Dirt_FallHeavy | Char_Mov_Gen_SHeel_Fall_Dirt_Hvy |  | 两脚几乎同时下 | 3
| 落地小 |  |  |  |  | done |  |  | Player_FS_StilettoHeel_Dirt_FallLand | Char_Mov_Gen_SHeel_Fall_Dirt_Lit |  | 听感通用，两脚稍错开下 | 3

## Music
序号ID | 类型Type | 场景类型Map | 地图玩法/背景说明Play Mode/ Background description | 主角状态故事进展描述 Description of the progress | 概念图 Concept | 负责策划 Designer | 是否需要区域/状态音乐变化 | 基本气氛情绪描述 | 反馈备注 Feedback | 状态 Status | 音效名 Sample Name | 音乐/环境声描述 | 是否有天气变化 | 是否有时间变化 | 参考视频名及描述 | 备注 | 区域说明图参考
示例行 | 场景音乐 | 例如：大世界/主城 | 例如：沙漠中的希望之洲，从颓败到重建繁荣。曾有过辉煌的历史。后遭到远征军入侵，逐渐颓败。现正处于重建的阶段。 大家在野外场景中自由争夺资源，并可击杀其他玩家。 |  |  |  | 城镇内： | 例如：热闹，欢快 |  | cancel to do 制作中 外包中 done | 音频设计师会按照相应规则填写 | 例如：带有鲜明的异域特色音乐。节奏较为活跃。主旋律鲜明突出
示例行 | 战斗音乐 | 例如：哥布林村落关卡 | 例如：猎人的居住地，地形为开阔峡谷，有瀑布、川流等。PVP副本打怪模式 |  |  |  | 例如：战斗前状态 例如：战斗触发后状态 例如：濒死状态 例如：死亡状态 | 例如：气氛静谧，略带阴森紧张 例如：紧张 例如：紧张度递增例如：失败，沮丧情绪